## Project Planner
Project Title
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Data Analysis Tool Development | 1 | 9 | 1 | 9 | 44%
Project Management | 1 | 3 | 1 | 3 | 100%
Project Plan | 1 | 1 | 1 | 2 | 100%
Software Design | 2 | 2 | 2 | 2 | 100%
Git Setup | 1 | 1 | 1 | 1 | 100%
Statistical Analysis and Presentation | 4 | 6 |  |  | 0%
Data Analysis Program | 4 | 4 |  |  | 0%
Testing Plan and Testing | 8 | 1 |  |  | 0%
Executive Summary | 9 | 1 |  |  | 0%
Updated Project Plan | 9 | 1 |  |  | 0%
Software Version Control | 4 | 5 |  |  | 0%